## Sheet1
# | Tasks | Subtasks | Status | Comments | Assigned To
1 | Login | Need AURA Service URL | Pending |  | Pandhari
|  | Need to Onboard Users onto AURA | Pending |  | Pandhari
|  | Need Handshake details from AURA (request / response) | Pending |  | Pandhari
2 | Trade Monitoring Page | Align the Primary Search Criteria horizontally
Add all the columns in the result table as per screenshots
Add Advanced Search Link
Double click on table row, it should: 1. Call a RESTFul service by passing TradeID 2. Accept JSON o/p from WS call, open a popup with Trade Details screen
"ERR" status row should be displayed in RED color
Resultant Table should display 100 records at a time and add pagination functionality if the no.of records exceeds 100.
Current Dataset should highlight all statuses (NEW,NMT,MTH,ERR)
3 | Trade Details Page | Display Data as per JSON o/p from the service call
Match the fields as per screenshots
This screen should have "ReSend" button
OnClick of "ReSend" Button, it should call a RESTFul service
4 | Navigation Bar | Left pane Navigation bar which will have all the navigation on the LHS of the page.
It should be a Tree like structure
5 | RESTFul Service skeleton | Design a JAX-RS Service to serve the "Search" functionality with o/p as JSON | In Progress |  | Kenil
|  | Design a JAX-RS Service to serve the "ReSend" functionality with o/p as JSON | In Progress |  | Kenil
6 | EJB Design | Develop Stateless EJB's which will serve DB requests | New |  | Kenil
|  | Develop using EclipseLink / JPA framework | New |  | Kenil
7 | DB / Stored Procedure (SP) Analysis | Get the count of SP's relevant to TRAX | New |  | Ajay
8 |  | Get SP's IN / OUT Params to check the compatibility with Java Services unlike Power Builder | In Progress |  | Ajay
9 |  | Get Tables details where transaction data is stored | New |  | Ajay
10 | Documentation | HLD |  | Initial Draft Given to Pandhari | Kenil
|  | LLD |  | Initial Draft Given to Pandhari | Kenil
|  | Setup Document | In Progress |  | Shubhnish
11 | Code Cleanup
Note on D1: Status Can be: New Pending In Progress Completed